## Sheet1
Thing to do | Admin view | User View | Rollout order | In old code | Who? | State | Notes
Navigation & Accounts
Design page w. static nav |  | 1 | 1 | Y | Betty | Done
Login | 1 | 1 | 1 | Y | Jon |  | preferably as a popover or drop down from sidebar |  | Betty | 1
User Profile |  | 1 | 1 | Y | Jon | 1/2 Done | needs to link to Jon's fixes |  | Jon | 17
User Bio |  | 1 | 2 | Y | Jon |  |  |  | Marcus | 7
Login Check on all Bidding |  | 1 | 1 | Y | Jon | 1/2 Done |  |  | Hunter | 0
Login Check on any Editing by regular user |  | 1 |  | Y | X | trivial, done |  | order\ | total | assigned | unassigned
Custom Home Page |  | 1 | 1 | Y | Jon |  |  | 1 | 21 | 18 | 3
Connection highly editable static content in a page | ? | 1 | 1 | N |  |  |  | 2 | 25 | 7 | 18
Forgot Password self-fix |  | 1 | 1 | Y | Jon |  |  | 3 | 9 | 0 | 9
[8 empty] | 4 | 3 | 0 | 3
Bidding
Class bid/edit existing draft |  | 1 | 1 | Y | Jon | Done | These are permutations of the same thing, so fairly cut/copy/paste-able
Act bid/edit existing draft |  | 1 | 1 | Y | Jon | Done
Panel idea bid/edit existing draft |  | 1 | 1 | Y | Jon | Done
Vendor bid/edit existing draft |  | 1 | 1 | N | Jon | Done
Ad bid/edit existing draft |  | 1 | 1 | N | Jon
Art bid/edit existing draft |  | 1 | 2 | N | Jon
Costume bid/edit existing draft |  | 1 | 2 | N | Jon | ??
Volunteer as panelist |  | 1 | 2 | Y | Jon
Delete Draft | 1- for other users | 1 - for self | 2 | N
Review & Accept Class/Panel | 1 |  | 2 | Y |  |  | Very similar
Review, Accept, & Cast Acts | 1 |  | 2 | Y
Approve Vendors & Ads | 1 | 1 | 3 | N |  |  | includes change to page for ad display
Approve Costumes | 1 |  | 3 | N |  |  | very similar, and simpler than 24/25
Approve Art | 1 |  | 3 | N
Set Act Tech Info & Pick Rehearsal |  | 1 | 3 | Y
Paying
Can't submit bid until paid |  | 1 | 1 | Y | Marcus
Hook bid to registration fee | 1 |  | 2 | N | Marcus
Connect Fee(s) to Scheduled Item(s) | 1 |  | 1 | Y | Marcus
Ticket Sales View | 1 |  | 2 | Y | Marcus
Attendance Report | 1 |  | 2 | Y | Marcus
Sync Ticket Types | 1 |  | 1 |  | Marcus
Sync Ticket Sales | 1* |  | 1 | Y | Marcus
User Admin
User Role/Privilege Grant | 1 |  | 1 | Y | Jon | Done
Reset Password | 1 |  | 1 | N | Jon
Impersonate | 1 |  | 1 | Y | Jon
View User Ticket Status | 1 |  | 2 | Y
View User Bids by User | 1 |  | 1 | Y
View User Schedule | 1 |  | 2 | Y
Delete User | 1 |  | 2 | Y
Set User Profile | 1 |  | 2 | Y
Scheduling
Schedule Class/Panel (from a bid) | 1 |  | 2 | Y*
Schedule Spontaneous (not bid) Event | 1 |  | 2 | Y*
Connect Tech To Shows | 1 |  | 2 | Y*
Cancel Event | 1 |  | 2 | Y*
Clone Event | 1 |  | 3 | N
Set event participation settings | 1 |  | 2 | Y*
Set/Change Presenter | 1 |  | 2 | Y*
Non-Staff Event View/Edit |  | 1 | 3 | Y*
Calendar for - show & special, conference, volunteer |  | 1 | 2 | Y
View of Calendar Item |  | 1 | 1 | Y
List of Items - show, conference, volunteer, special |  | 1 | 2 | Y
Show conference bios |  | 1 | 2 | Y
Show staff bios |  | 1 | 2 | Y
Show perfomer grid on shows |  | 1 | 2 | Y
Reporting
Bio Report | 1 |  | 3 | Y
Act Tech Info Report | 1 |  | 3 | Y
Calendar per User Report | 1 |  | 3 | Y
Attendee Report (paid & volunteer) | 1 |  | 4 | N
Room Report | 1 |  | 4 | Y
Ops per coordinator Report | 1 |  | 4 | Y*
Mail
needs big overhaul!
|  |  | 58 |  | 26 | 32